## IT Migration Plan
Christian Family Services (CFS)
Network Architecture Plan
. | . | . | . | . | . | state 0 | . | state 1 | . | state 2 | . | state 3 | . | state 4 | . | state 5 | state FiNAL | .
[6 empty] | Charter Modem EN2251 B522231F562 |  | Charter Modem EN2251 B522231F562 |  | Charter Modem EN2251 B522231F562 |  | Charter Modem EN2251 B522231F562 |  | Charter Modem EN2251 B522231F562 |  | Charter Modem EN2251 B522231F562 | Charter Modem EN2251 B522231F562
[8 empty] | UniFi Dream Router 7 $279 |  | UniFi Dream Router 7 $279 |  | UniFi Dream Router 7 $279 |  | UniFi Dream Router 7 $279 |  | UniFi Dream Router 7 $279 | UniFi Dream Router 7 $279
[6 empty] | Charter Router A92218330ADC 192.168.44.1 192.168.1.1 admin/admin |  | Charter Router A92218330ADC 192.168.44.1 192.168.1.1 admin/admin |  | remove |  | remove |  | remove |  | remove
[6 empty] | Netgear FS728TP switch 24 x 10/100 Mbps RJ-45 PoE, 2 x 1Gb Copper, 2 x 1Gb Combo SFP 192.168.44.13 192.168.0.239 admin/password |  | Netgear FS728TP switch 24 x 10/100 Mbps RJ-45 PoE, 2 x 1Gb Copper, 2 x 1Gb Combo SFP 192.168.44.13 192.168.0.239 admin/password |  | Netgear FS728TP switch 24 x 10/100 Mbps RJ-45 PoE, 2 x 1Gb Copper, 2 x 1Gb Combo SFP 192.168.44.13 192.168.0.239 admin/password |  | Netgear FS728TP switch 24 x 10/100 Mbps RJ-45 PoE, 2 x 1Gb Copper, 2 x 1Gb Combo SFP 192.168.44.13 192.168.0.239 admin/password |  | remove |  | remove
[14 empty] | UniFi switch $379 or $399 USW-24-POE or USW-Pro-Max-16-PoE |  | UniFi switch $379 USW-24-POE (95W) | UniFi switch $379 USW-24-POE (95W)
[6 empty] | PANDUIT patch panel |  | PANDUIT patch panel |  | PANDUIT patch panel |  | PANDUIT patch panel |  | PANDUIT patch panel |  | PANDUIT patch panel | PANDUIT patch panel
[6 empty] | APC Back-UPS CS 350 |  | APC Back-UPS CS 350 |  | APC Back-UPS CS 350 |  | APC Back-UPS CS 350 |  | APC Back-UPS CS 350 |  | APC Back-UPS CS 350 | APC Back-UPS CS 350
[6 empty] | MikroTik RouterBoard RB3011UiAS-RM 192.168.44.19 192.168.88.1 admin/<blank> |  | MikroTik RouterBoard RB3011UiAS-RM 192.168.44.19 192.168.88.1 admin/<blank> |  | MikroTik RouterBoard RB3011UiAS-RM 192.168.44.19 192.168.88.1 admin/<blank> |  | remove make sure it is not doing anything hidden such as static routing, DHCP reservations, VPN, or firewall rules |  | remove |  | remove
[6 empty] | CISCO ASA 5506-x firewall 192.168.1.1 |  | CISCO ASA 5506-x firewall 192.168.1.1 |  | CISCO ASA 5506-x firewall 192.168.1.1 |  | remove |  | remove |  | remove
[6 empty] | TP-Link wifi access point http://tplinkap.net or http://tplinkwifi.net admin/admin |  | TP-Link wifi access point http://tplinkap.net or http://tplinkwifi.net admin/admin |  | TP-Link wifi access point http://tplinkap.net or http://tplinkwifi.net admin/admin |  | remove confirm whether Wi-Fi clients are actually using it versus the Spectrum router |  | remove |  | remove
[6 empty] | Dell PowerEdge R720 5FH48Y1 |  | Dell PowerEdge R720 5FH48Y1 |  | Dell PowerEdge R720 5FH48Y1 |  | Dell PowerEdge R720 5FH48Y1 |  | Dell PowerEdge R720 5FH48Y1 |  | Dell PowerEdge R720 5FH48Y1 | New Server
[6 empty] | > CFSDC2 (Domain Controller) 192.168.44.60 |  | > CFSDC2 (Domain Controller) 192.168.44.60 |  | > CFSDC2 (Domain Controller) 192.168.44.60 |  | > CFSDC2 (Domain Controller) 192.168.44.60 |  | > CFSDC2 (Domain Controller) 192.168.44.60 |  | > CFSDC2 (Domain Controller) 192.168.44.60 | > CFSDC2 (Domain Controller) 192.168.44.60
[6 empty] | > CFSFS (File Server) 192.168.44.61 |  | > CFSFS (File Server) 192.168.44.61 |  | > CFSFS (File Server) 192.168.44.61 |  | > CFSFS (File Server) 192.168.44.61 |  | > CFSFS (File Server) 192.168.44.61 |  | > CFSFS (File Server) 192.168.44.61 | > CFSFS (File Server) 192.168.44.61
[6 empty] | > CFSPRN (Print Server) 192.168.44.62 |  | > CFSPRN (Print Server) 192.168.44.62 |  | > CFSPRN (Print Server) 192.168.44.62 |  | > CFSPRN (Print Server) 192.168.44.62 |  | > CFSPRN (Print Server) 192.168.44.62 |  | > CFSPRN (Print Server) 192.168.44.62 | > CFSPRN (Print Server) 192.168.44.62
[6 empty] | > VJUMP (Jump Box/Admin VM) 192.168.44.30 |  | > VJUMP (Jump Box/Admin VM) 192.168.44.30 |  | > VJUMP (Jump Box/Admin VM) 192.168.44.30 |  | > VJUMP (Jump Box/Admin VM) 192.168.44.30 |  | > VJUMP (Jump Box/Admin VM) 192.168.44.30 |  | > VJUMP (Jump Box/Admin VM) 192.168.44.30 | > VJUMP (Jump Box/Admin VM) 192.168.44.30
[6 empty] | This is the current state of the CFS IT network architecture as of March 14, 2026. |  | DISCOVER PHASE. Document DHCP, NAT, Wi-Fi source, firewall rules, VPNs, and any special dependencies. Should not use UniFi DR7 and Charter/Spectrum router concurrently for very long. Deploy a UniFi router between the Charter/Spectrum modem and router. This will give greater visibility into the network, showing IP VLANs and other critical configurations. Will also help determine if WIFi is broadcast from Charter/Spectrum router or via TP-Link AP. > capture any static IP reservations > note any VPNs |  | CUTOVER. Remove the Charter/Spectrum router. Should no longer be needed and migrate to UniFi DR7. This should continue to increase visibility into network architecture and usage. |  | SIMPLIFY. Remove redundant and unnecessary equipment. The RouterBOARD and Cisco ASA 5506-x firewall functionality should exist in the UniFi DR7 (firewall and security) NOTE: Do not remove MikroTik or ASA until all active services/rules are verified and replicated if needed. |  | PERFORMANCE UPGRADE. Replace the old and slow Netgear FS728TP switch with a modern UniFi USW-24-POE switch. |  | Eventually will need to upgrade and replace this Dell PowerEdge R720 server. Currently it has a bad harddrive and is old and outdated, but need to be careful with migration. Determine: backups, VM host configuration, file shares and permissions, print services, AD/DNS dependencies | Spectrum modem → UniFi DR7 → new UniFi switch → AP / server / clients

## 2nd Floor IT
. | .

## 1st Floor IT
.
Dell PowerEdge R720
5FH48Y1

## Sheet1
. | . | state 0 | . | . | ….. | …
Charter Modem EN2251 B522231F562
Charter Router A92218330ADC 192.168.44.?? 192.168.1.1 admin/admin??
Netgear FS728TP switch 24 x 10/100 Mbps RJ-45 PoE, 2 x 1Gb Copper, 2 x 1Gb Combo SFP 192.168.44.13 192.168.0.239 admin/password
PANDUIT patch panel
APC Back-UPS CS 350
MikroTik RouterBoard RB3011UiAS-RM 192.168.44.19
CISCO ASA 5506-x firewall 192.168.1.1
TP-Link wifi access point
Dell PowerEdge R720 5FH48Y1
> CFSDC2 (Domain Controller) 192.168.44.60
> CFSFS (File Server) 192.168.44.61
> CFSPRN (Print Server) 192.168.44.62
> VJUMP (Jump Box/Admin VM) 192.168.44.30
This is the current state of the CFS IT network architecture as of March 14, 2026.

## ServiceProviders
.